## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge |  | Status | Updated | Update Details
1 | UI | Home screen | Manager, User | This screen is display some information,products. | Đức Anh | To Do | iter1 | none | https://docs.google.com/document/d/1IzDSbDuQVY3Finj3_Grz_CR6qWx9NzrQbHCU7hgw0_A/edit
2 | Database | Data | Manager | Project database | Quân + Group | To Do | iter1 | none | https://docs.google.com/document/d/1WFKiXqde5o9jbPm401PXeNjurTrTRhNAL46Kt14G4H4/edit?usp=sharing
3 | Github | Work in group | Team | Github for teammate working | Mai Chí Thanh | To Do | iter1 | none | https://github.com/xxxNartC/ISP392
4 | User Login | Common | User,Manager | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | Mai Chí Thanh | Done | iter1 | none | https://docs.google.com/document/d/1uR8Wa37VKdzL6MKbY2WpgyXZ-pohtYIEP9kJvjagS8g/edit
5 | DashBoard | Common | Manager | Displays general information and key metrics from a variety of sources | Đạt | To Do | iter1 | none | https://docs.google.com/document/d/1jLynhiWinSjbPOb8pthOvRFiL4Gp9B2iNE9bxL08Xao/edit
6 | Register | Common | User | 'This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | Chu Tứ | Done | iter1 | none | https://docs.google.com/document/d/14Bhk4oT0caZoPd4lkuZ2EpJp1fUrS1YcKfLYloj8MGU/edit
7 | PreOrderTable | System view | User | Pre-order table | Quân | To Do | iter1 | none | https://docs.google.com/document/d/1IzDSbDuQVY3Finj3_Grz_CR6qWx9NzrQbHCU7hgw0_A/edit

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4